REQUEST FOR PROPOSAL for

CAD, RMS and Mobile Replacement Project

# ATTACHMENT I

# SCOPE OF SERVICES

TABLE OF Contents

1	SCOPE OF SERVICES	1

1.1	Background Information	1

1.1.1	The Community	1

1.1.2	Sizing Information Summary	1

1.1.3	Current CAD & Police RMS System	2

1.2	Project Goals	2

1.2.1	CAD, RMS and Mobile Systems Objectives	2

1.3	Services	3

1.3.1	Project Management Services	3

1.3.2	Project Schedule	3

1.3.3	Contractor Project Staffing Plan	4

1.3.4	Project Reporting	4

1.3.5	Project Status Reports	4

1.3.6	Implementation Management Plan	5

1.3.7	Training	5

1.3.8	Data Conversion Study	6

1.3.9	Operational Migration Plan	7

1.4	General Software Requirements	7

1.4.1	GIS Requirements	7

1.4.2	Browser Based Functionality	7

1.4.3	Data Purging	8

1.4.4	Back-up and Recovery	8

1.4.5	CAD Stand-Alone Mode	8

1.4.6	Automatic Update of Workstations/MDCs	8

1.4.7	Data Integrity	8

1.4.8	Coding	8

1.4.9	Scalability	9

1.4.10	Flexibility	9

1.4.11	System Reliability/Availability and Access	9

1.4.12	System Administration	9

1.4.13	Database Administration	10

1.4.14	Security	10

1.4.15	Security Requirements	10

1.4.16	Application Security Coding Requirements	11

1.4.17	National & State Public Safety Data Standards	12

1.5	CAD Software Requirements	14

1.6	MDC Software Requirements	15

1.7	RMS Software Requirements	16

1.8	Interface Software Requirements	17

1.8.1	ANI/ALI	17

1.8.2	Alarm Monitoring Company Public Safety Answering Point	18

1.8.3	License Plate Reader – Vigilant Solutions	18

1.8.4	Radio Console Interface / Push to Talk	18

1.8.5	Global Positioning System (GPS) / Automatic Vehicle Location (AVL)	19

1.8.6	Records Check System	19

1.8.7	California Dept of Justice CLETS	19

1.8.8	Orange County Automated Telecommunications System (“OCATS”)	20

1.8.9	Law Enforcement Information Exchange (“LInX”)	20`

1.8.10	California Dept of Justice - Cal-Photo	21

1.8.11	California Dept of Corrections and Rehabilitation - Parole LEADS	21

1.8.12	Forensic Logic (formerly CopLink)	21

1.8.13	Crossroads Software – Citation, Analytics and Report Writing	21

1.8.14	License Plate Reader – Vigilant Solutions	21

1.8.15	California Highway Patrol - Allied Agencies to SWITRS Reporting Services	22

1.8.16	LiveScan	22

1.8.17	Lexis Nexis – Desk Officer Reporting System	22

1.8.18	Orange County District Attorney – Electronic Direction for Compliant	22

1.8.19	Video Management System	22

1.8.20	Body Warn Camera / Dash Mount Camera Metadata Tagging	22

1.8.21	CAD-to-CAD Interface	23

1.8.22	Tow Provider Interface	23

1.9	System Testing, Reliability and Acceptance	23

1.9.1	System Test Period	24

1.9.2	System Reliability Period	25

1.9.3	Final System Acceptance	25

1.10	Hardware Requirements	25

1.10.1	CAD Servers:	26

1.10.2	Workstations	27

1.10.3	Position Requirements	27

1.10.4	CAD Printers	27

1.11	Licenses	27

1.12	Maintenance, Support and Updates	27

1.13	Warrant	27

1.14	Quality Control	28

Attachment A:  City Technology Standards	29

Attachment B:  City GIS Standards	32

# SCOPE OF SERVICES

## Background Information

### The Community

The City of Irvine, located Orange County, CA was formally incorporated in 1971.  The City was formed as a master planned community encompassing many residential villages; commercial centers particularly in the technology and semiconductor sectors with many having their national headquarters within the city; religious institutions and educational institutions such as the University of California Irvine, Concordia University, Brandman University, and satellite campuses for numerous colleges, including University of Southern California, California State University Fullerton, University of La Verne and Pepperdine University – just to name a few.

Fire protection in Irvine is provided by the Orange County Fire Authority (“OCFA”) with ambulance service by a private contractor.  Law enforcement is provided by the Irvine Police Department (“IPD”), staffed with approximately 232 sworn officers and 244 non-sworn personnel.  The City of Irvine is rated as having one of the lowest violent crime rates among larger cities (population over 100,000 to 499,999).  Irvine’s 2019 population estimated to be at least 285,000 with continued growth over the next two decades that will likely make Irvine the largest city in Orange County, California.

The agency’s Communications Bureau, located at Police Headquarters (1 Civic Center Plaza, Irvine, CA 92606) provides a central service point for responding to both emergency and non-emergency calls for police and animal services with emergency calls taking preference.  Staffing consists of 16 full-time dispatchers, 5 supervisors and 1 part-time dispatcher each of whom are committed to providing exceptional service to the public.

The Communications Bureau receives an average of 200,000 phone calls annually.  The Communications Bureau operates with state-of-the-art equipment, including a computer aided dispatch system, GPS automatic vehicle location system, intelligent phone workstations and an 800 MHz trunked radio system.  The center is also equipped with a video wall that allows dispatchers to view live video from a closed-circuit TV system, as well as from nearly 130 traffic intersection cameras located throughout the City.  This innovative feature helps dispatchers to be more proactive in their duties by providing deployed resources with updates they may be obtaining visually.

### Sizing Information Summary

The following information is being provided with the sole purpose of assisting the Contractors in sizing the correct solution within their proposals.

| Public Safety Employees | Police |
| --- | --- |
| Sworn Employees | 232 |
| Auxiliary Officers | 2 |
| Civilian Employees | 241 |
| Total Employee Count | 475 |
| CAD Access Equipment | Police |
| Dispatch and Call Taking | 8 |
| Mobile Computers | 82 |
| Desktop Computers w CAD Access | 16 |
| Desktop Computers w PD RMS Access | 300 |
| Public Safety Stats | Police |
| Calls for Service | 187,042 |
| Dispatched Responses, Police & Fire | 187.042 |

### Current CAD & Police RMS System

IPD currently utilizes disparate systems to include; Hexagon’s I/CAD products, Hexagon’s Ileads for records management, Tritech’s Copperfire for report writing, DIMS for digital evidence management, Crossroads for citation and accidents reporting and Hyland’s OnBase for case and records management.

Approximately 90% of Public Safety staff use the following systems: CAD dispatcher, CAD mobile, CAD web, California Law Enforcement Telecommunication System (“CLETS”) interface, jail management, property and evidence management, report writing, investigations, case management, records management, records archiving, custom reports, and database management.

Although the City intends to evaluate the Contractor’s total solution for CAD / RMS and Mobile, existing Sub-systems may require integration in the event the Contractors solution does not meet the functionality requirements.   These subsystems include a citation and accident reporting application called Crossroads.

The Police Department headquarters and substations are interconnected via fiber and traditional T1 circuits, but the network backbone is primarily 1GB to the desktops.  The City standardized with Dell for the desktop computers and Dell OptiPlex 7010 workstations for all the dispatch console positions (all desktops and workstations run Windows 7 Pro 32bit and 64bit).  Computer systems are refreshed every three years and MDC’s every five years.  All networking equipment is Brocade, which may be replace by CISCO and all servers are HP.

The existing CAD system consists of 7 servers (one physical and 6 virtual).  It is the City’s desire to implement a new CAD system that is virtual, or Cloud based.  The City uses VMWare’s product and plans to remain with VMWare for virtualization.  The existing Dell interface servers maintain interfaces for CLETS and ALI-ANI.

Servers run Win2k8.  The City’s Directory Services/Domain are planned to be upgraded to either Windows 2008 or Windows 2012.  The City’s database standard is Microsoft SQL.

## Project Goals

With a new CAD and RMS, the City’s ability to prevent, respond to, manage, and analyze situations threatening the safety and property of citizens, and provide other critical emergency services resources will be significantly enhanced.  An integrated Police and RMS System will lay the foundation for intelligence led policing, enhanced criminal justice, and overall strategic public safety resource deployment.

The system must advance the overall mission, goals, and objectives of the City by making public safety personnel more effective in preventing, combating, and responding to public safety matters through strategic resource deployment.

The City is aware of current industry technologies and is seeking a balance between mainstream and state-of-the-art technology.  The City wants to employ solutions that will prolong the life of the new system and postpone the need for replacement.  The City envisions that the system will be based upon current, proven technology that is derived from current industry and City standards.

### CAD, RMS and Mobile Systems Objectives

The system must be able to perform so that an operator will not have to wait for critical information and will rarely have to wait for routine information.

The system must utilize an easily understandable user interface that optimizes efficiency and the viewing of critical data in real time.  Users must be able to filter information according to their preferences utilizing the mouse, hot keys and/or command line functionality.  All critical functions must be accessible via the keyboard, as mousing between entries is discouraged.

The system must be easily configurable and permit the System Administrator to create, update, and manage the key records and tables, dialog boxes, status monitors, and masks, as well as create, modify, and, print reports.

The proposed solution must adhere to City’s technology standards.  The standards are consistent with those being adopted by public safety entities throughout the country, as well as with the interoperability standards adopted by the US Federal government.  The “City Technology Standards” is being provided as Attachment “A” within this RFP.

The system must be in compliance with Section 508 of the Rehabilitation Act of 1973, as amended (29 U.S.C.  §792).

The City is increasingly adopting the .Net platform for new development and interfaces utilizing XML-based web services.  Thin client applications are preferred.  This consideration is critical for new and upgraded applications in the public safety arena where appropriate.

The underlying IT Infrastructure (Network, Computer, Storage) must be built on the WINTEL Platform (current version minus one), the database must be MS SQL Server, and capable of virtualization with VMware's ESX hypervisor platform.  The underlying storage must offer three tiers of block level storage; Solid-State Drive (“SSD”), Serial-Attached Storage (“SAS”), Serial AT Attachment (“SATA”) and dynamically move data between each tier based on access frequency.

## Services

### Project Management Services

Major City information technology projects, including the CAD, RMS and Mobile Replacement project, are managed by Contractor specific subject matter experts (“SME”) and project managers reporting to the City Project Manager as the primary lead in this project.  Project sponsorship is through business units and City resources for the project are staffed and managed through a matrix management project structure.  A project steering committee will oversee the CAD, RMS and Mobile project.  The City expects significant project management activities to include, but not be limited to, Project Scheduling, Risk Management, Cost Management, Change Control Management, Communications Management and on-site meetings as (and when) required.

Prior to contract signing, the Contractor will prepare and submit to the City Project Manager for approval a Statement of Work to include;

- Draft proposed schedule,

- All features of Contractors base system that are available in the base system price

- All features request via the functional matrix and the cost of each

- Annual maintenance costs, and

- Final Implementation Plan

### Project Schedule

Contractor must provide draft project schedule in Microsoft Project format utilizing a Work Breakdown Structure (“WBS”) format including resources and milestones.  The intent of the City is to develop and maintain a shared project schedule that includes all Contractor and City tasks and activities.  Implementation schedule should incorporate the major subproject implementation phases such as CAD, RMS, Mobile, etc.

### Contractor Project Staffing Plan

Given the high-profile nature of this project, the City expects best in class project management services from the Contractor.  The City expects the Contractor will work closely in conjunction with City’s Project Manager.  The City will only accept Contractor personnel who have significant and relevant experience with the Contractor’s CAD, RMS and Mobile system and can show a successful track record at locations of similar size and complexity as the City.

Contractor shall:

- Identity proposed staffing resources and level of effort for each major task.  Contractor must also include an organization chart for proposed project personnel, including proposed sub-contractors.

- Describe expectation of City staffing resources and Level of Effort for each major phase, including expected skill set needed to successfully complete each task.

- List key personnel that will be assigned to the project.

- Provide resumes of all key staff that provides enough information to allow the City to evaluate their capability and qualifications to perform proposed tasks.

- Describe roles and tasks for all key personnel for each major phase of the project,

- Identify whether this is their major assignment, and a projection of other assignments they may be working on during the implementation period.

- Describe for all key personnel what percentage of time will be on project.

- Provide information regarding who will be on site for each major phase of the project, and who will be remote.

- Provide the Contractor’s escalation process of issues.

- Describe facilities and equipment that the City is required to provide on-site staff.

- Submit all Contractor personnel assigned to work on-site on the CAD, RMS and Mobile project to undergo a criminal history check.  Off-site personnel may also be subject to a criminal history check.  Please note that arrangements for required criminal history checks should be made in advance with appropriate City personnel.  The City reserves the right to reject any personnel proposed by the Contractor for any reason.  All key personnel will be required to sign a confidentiality agreement for access to sensitive data.

- Ensure that support personnel proposed have the necessary level of training and experience with the application suite to ensure that the City is receiving expert-level support.  The Contractor may be requested to provide the City with a listing of all certificates, training courses and other relevant evidence to document the level of expertise of proposed support personnel.

- Understand that the Contractor’s Project Manager is expected to coordinate and participate in all activities related to Contractor demonstrations, if shortlisted.

### Project Reporting

The Contractor shall participate, at a minimum, in a bi-weekly Project Meeting to report progress toward contract deliverables, update status from the previous reporting period, and advise current objectives, problems or delay issues, proposed corrections and other relevant information.

### Project Status Reports

The Contractor’s Project Manager will provide, at a minimum, bi-weekly project status reports detailing relevant information to the City’s Project Manager.

### Implementation Management Plan

The City uses the Project Management Book of Knowledge (“PMBOK”) as a guide for implementation of all projects.  Please provide how the Contractor’s implementation planning activities incorporate all of the major PMBOK phases: Initiation, Planning Execution, Monitoring & Control, and Closing.  For each phase, Contractor shall:

- Provide the Contractor’s process to complete each major phase (i.e.  CAD, RMS, Mobile, AFR, etc.);

- Provide the Contractor’s methodology to prepare servers (i.e., completed on-site or at the Contractor’s location);

- Provide the Contractor’s Deployment plan of all phases and why this methodology is being proposed;

- Provide the Contractor’s Risk Management plan that will be used to ensure successful implementation of all phases;

- Provide the Contractor’s Quality Management plan that will be used to ensure successful implementation of all phases; and

- Provide any Change Management solutions provided by the Contractor that are a component of the proposal.

### Training

The Contractor shall develop a training work plan and curriculum to be approved by the City project manager in conjunction with City personnel.  The work plan should also include periodic follow-up and update training when a new release or version of any application is installed.  The Contractor must develop a training plan and curriculum that specifies the required training and technical staff supporting the application.  The Contractor’s City-approved training schedule must be closely coordinated with City staff to coincide with the installation of the software and hardware.  Upon acceptance by the City Project Manager, the Contractor shall implement said approved plan.

The City requires a hybrid training approach that utilizes both Contractor-supplied trainers, as well as a train-the-trainer capability.  All initial CAD, RMS and Mobile training shall be performed by Contractor training City personnel as trainers.  Thereafter, the Contractor will shadow a training session conducted by the City trainers, who will become responsible for completing the rest of the training sessions.  The shadow period is expected to run for one (1) class for each training type (dispatchers, records, field personnel and administrators).

The City requires an optional provision to have each of the dispatchers trained by the Contractor, as opposed to a train-the-trainer approach.  This option will be determined at the time training is to commence and will be based on the comfort level of the project team.

The City will work with and assist the Contractor in the scheduling of the initial shadow training programs.  The City shall provide space adequate for conducting the training and housing and securing the training equipment.

Given the shift assignments of public safety personnel, training courses will often need to be scheduled outside of normal working hours, including weekends and evenings.  In order to keep the training relevant to the ultimate system look-and-feel, as well as fresh as possible and still accommodate the necessary number of sessions, it is expected that training will not begin until after preliminary system acceptance and before cut-over, but in no case will begin longer than 30 days prior to the scheduled “Go-live” date.

If the system Go-live date is significantly delayed due to the Contractor’s actions or faults, any repeat training sessions as determined by the City must be performed at no cost to the City.

With some exceptions (e.g.  System Administration training), classes will contain no more than 6 trainees for CAD training and no more than 12 trainees for RMS and Mobile systems and will not last longer than eight hours.

The Contractor shall be responsible for providing training materials and take-away documents such as user manuals and user guides and cheat sheets to adequately perform the initial training and provide follow-up reference material for the trainees.  These documents should also be provided in an electronic format.

The Contractor must provide a comprehensive training program minimally covering:

- PSAP personnel user training;

- Police field personnel;

- Agency-Based supervisory personnel;

- Standard and ad hoc reporting;

- Records personnel

- CAD/RMS/Mobile system administration (including Contractor supplied Interfaces);

- CAD technical Operations; and

- GIS Functions and Operation

### Data Conversion Study

It is the City’s desire to have historical data from CAD and RMS systems accessible, resident or not, within the new CAD, RMS and Mobile solution.  It is imperative that all historical data is either archived or maintained in a manner that allows querying of the data from the new proposed system or is converted and added to the new proposed system.

Contractors are encouraged to use their expertise in this area to provide the City applicable options in the form of a Data Conversion Study.  The City understands there may be many methodologies available to manage legacy data in a cost-effective and user-friendly manner.  The City is seeking to migrate the following data from the legacy systems:

- Incidents,

- Incident Premise History,

- Case Reports,

- Case Narratives,

- Case Persons,

- Case Property,

- Case Vehicles,

- Arrests and Associated Booking records,

- Case Attachments,

- Historical Case Report Requests,

- Field Interviews,

- Citations Data and Attachments,

- Accident Reports and Attachments,

- Pawns

- Equipment Lists,

- Personnel Data,

- Master Name Index,

- Master Property Index, and

- Master Locations Index,

The Contractor shall include a description of all Contractor and City processes and activities required to successfully migrate legacy data from the legacy systems into the Contractor’s proposed solution.  The study should include the following:

- The Contractor’s proposed data conversion process;

- Specific functionality and features of the proposed solutions(s).  For example, precise information how City personnel would access the historical data;

- Specific roles and responsibilities for proposed City resources, as well as recommended skills of personnel required to perform City tasks;

- Specific roles and responsibilities for proposed Contractor resources, as well as recommended skills of personnel required to perform City tasks;

- Qualification, experience and resumes of Contractor staff proposed for the Data Conversion Task;

- A description of the Contractor’s proposed automated data conversion tools;

- Recommended solutions for end-users to access non-migrated legacy data via integrated system or separate queries;

- Recommended storage location for non-migrated legacy data;

- Any prior data conversion experience with the City’s legacy systems.  Please list the relevant projects, the versions involved, and provide contact information for the clients.  We are particularly interested in projects that involved the proposed Data Conversion personnel; and

- The Contractor shall include a description of its process for implementing data conversion and archiving legacy data.

### Operational Migration Plan

The migration from one CAD, RMS and Mobile system to a new one can present significant threats to the health and safety of the public and first responders if problems arise.  The City CAD cutover will take place in its existing Communications Center and will require an extraordinary level of coordination and staging to avoid impacting existing operations.

Cut-over activities shall be approved in advance by the City.  A cut-over working group composed of City, CAD, RMS and Mobile Contractor and other relevant personnel will be formed to develop a detailed migration plan and the actual execution of the CAD, RMS and Mobile system cut-over.

## General Software Requirements

### GIS Requirements

The City uses an ESRI GIS database.  Contractors must interface with this database to develop the geo-file required for the proposed systems.  The interface should be designed to load an initial file from the City’s GIS and to also periodically enable updates of CAD, RMS and Mobile system’s geo-file from the City’s GIS database.  The Contractor must provide the tools necessary for City GIS staff to perform the geo-file creation and upload process.  Specific details of the City’s GIS Services are outlined within this RFP in “Attachment “B”, City GIS Services”

### Browser Based Functionality

The proposed solution must include browser-based functionality.  This functionality allows authorized staff to access the system from non-dispatch or call taking terminals utilizing a thick client.  The browser-based functionality must include:

- The ability to see all CAD activity in real time;

- The ability to see the CAD GIS map, including available units, units on calls, calls holding, active calls, etc.;

- The ability to send and receive messages within the system, including individuals, units, dispatch positions, call taking positions, etc.; and

- The ability to access information within the system, including all call information, all unit information, all timestamps, all AVL/GPS data and routing information to any location.

### Data Purging

The system must have a purge facility that will off-load data from the servers for archival storage, access, and/or destruction.  Purging must be administrator-configurable by multiple parameters.  All purges must be subject to strict audit tracking and reporting and must occur while the system is fully operational, without degradation of performance.

### Back-up and Recovery

The servers must have an appropriate automated back-up capability for system and application back-up and transactional level recovery.  Back-up media shall be in a format suitable for convenient off-site storage.  The system must provide differential back-up schedules for various system components and be configurable by the system administrator.  Incremental and full back-up capabilities must be provided.  All back-up and recovery processes must be subject to auditing and reporting.  System back-ups must be accomplished without taking the application out of service and without degradation of performance or disruption to operations.

The City desires to utilize its existing backup system to perform all necessary backups providing for full-restore should an event occur that requires it.  A full restore means that all primary and ancillary systems that are being backed up are restored and fully functional.  If specific backup parameters are required by the Contractor, please describe those requirements in detail.  If the proposal includes backup alternatives, it is required to specify the system, cost, and methodologies that will be used to accomplish the back-up and recovery of the system.

The City’s current Back-Up and Recovery Software and process is more fully described in the “City Technology Standards” being provided as Attachment “A” within this RFP.

### CAD Stand-Alone Mode

The CAD workstations must have the ability to operate in a stand-alone, off-line mode in the event the CAD servers become unavailable.  At a minimum, the system must provide the ability to track basic unit availability and status information in a standalone mode.

### Automatic Update of Workstations/MDCs

All software updates to both desktop CAD and RMS workstations and MDC computer terminals must be accomplished through an automated network facility and not require a technician to perform a manual procedure on each workstation/MDC.  This update utility must be configurable by multiple parameters, e.g., workstation type, and able to support the scheduling of update activities in batch and non-batch modes.  A summary report is required, documenting the results of the update activity.

### Data Integrity

The system must ensure the integrity of the data which it maintains.  Interruptions in processing due to incidents such as aborted transactions, hardware failures, or network unavailability must not result in inaccurate or inconsistent data in the system.  If data transfers occur, the system must provide a method of audit validation to ensure that all data sent was received in the target application.

### Coding

The system shall be developed utilizing a current programming language such as .NET Framework, ASP.NET MVC, or other language acceptable to the City.  The City requires Contractors to actively advance development technologies as provided by industry standards and not maintain any portion of the proposed solution with technology that is outdated, end of life, end of support, etc.  The Contractor must disclose the programming language used in the proposed solution.

### Scalability

Future requirements for regional cooperation and interoperability will only increase.  Since this may result in the system being subjected to a greater than normal amount of traffic, the system must be able to scale up to handle the additional load without any performance impact, specifically on the CAD operations.  Increased loads of up to 50 percent may be the result of temporary surges based on a major event.  Also, the need may arise to permanently increase the standard capabilities of the system.  The former will be handled by building in excess capacity over historical trends, the latter by seamlessly adding hardware and software components to adapt to the new workload.  Adding or upgrading hardware components must be accomplished without bringing the system down or negatively affecting its performance.

### Flexibility

The system shall be able to retain its performance levels when adding additional users, functions and data.  The solution functionality and associated business rules must be able to be configured with the use of applications or functions that do not require "code" modifications.  The screens shall be highly configurable, providing ability to reposition and rename field labels, remove or “turn-off” unused fields, maintain data, and allow the addition of user-defined fields.  The system shall provide the ability to create and/or modify business rules.

### System Reliability/Availability and Access

The public safety mission requires consistent operations, at a minimum 99.999% up time.  Routine maintenance or administrative procedures must not require system “down-time” or a re-start to take effect.

### System Administration

The proposed solution must provide a suite of system administration tools to support the effective ongoing operation of the systems.  The full suite of system administration tools shall be available to appropriate City personnel.  System administration capabilities, at a minimum, must include the ability to:

- Create and maintain user and group accounts;

- Integrate with Active Directory to allow for single sign on;

- Manage security (as described below);

- Manage back-up and recovery processes;

- Monitor and tune system performance;

- Install and configure hardware;

- Install and configure software/updates;

- Interface with ESRI Web Services and google maps for updating CAD geo data;

- Monitor and maintain interfaces;

- Schedule procedures (staff, assignments);

- Schedule report distribution;

- Manage disaster recovery procedures;

- Configure alerts;

- Organize and maintain system documentation; and

- Perform remote management.

The systems must allow the System Administrator to configure by jurisdiction, agency, or user group the display of all available information, including maps, status screens, event forms, call entry screen, dispatch screens, and pull-down menus.  Changes to one agency/jurisdiction/user-group configuration must not affect any other agency/jurisdiction/user-group configurations.

The System Administrator must be able to modify the layout and data elements displayed on all Contractor supplied forms and screen masks, and the ability to create macros or shortcuts for common user functions.

The System Administrator or other authorized user must also be able to add a report, macro, or function to the application menu and add new data elements to forms or report formats.

All system administration procedures must be supported by a detailed logging, auditing and reporting capability.

### Database Administration

The full suite of database administration tools and capabilities for the system must be available to the City.  These include, but are not limited to, the ability to:

- Alter on-screen field attributes, i.e., positioning, labels, drop-down lists;

- Specify edit and validation checks on fields;

- Modify content of drop-down lists; radio button lists, etc.;

- Perform system diagnostics;

- Monitor and tune database performance;

- Perform database back-up and recovery;

- Execute queries;

- Download data directly into Microsoft Excel, Microsoft Access, and SQL Server format;

- Support integration via web services;

- Configure alerts; and

- Log and archive all database activity.

Database imports and exports must be accomplished with minimal impact on system performance and must maintain the integrity of all relational linkages.  Import/export tools must support both automated and ad hoc operations.

All database administration procedures must be supported by a detailed logging, auditing and reporting capability.  Changes to one agency/jurisdiction/user-group configuration must not affect any other agency/jurisdiction/user-group configurations.

### Security

A mission-critical application affecting the safety of the public, as well as the City’s first responders, the system must be supported by robust security controls.  Security considerations to be addressed minimally include: hardware and networks; application security; user identification and authentication; and multi-jurisdictional considerations.

Multiple firewalls, encryption, anti-virus software, intrusion detection, advanced authentication for remote users and LDAP authentication are all utilized within the existing City’s systems.  Software must support the City’s virus scanning software.

All hardware implemented within the City networks must go through a security review and be certified by the City Information Services Manager for compliance with the City standards.

### Security Requirements

The system/security administrator must have, at a minimum, the ability to assign different user profiles based on individual and group classifications and sub-classifications and assign differential access privileges.  To protect HIPAA, CJIS and other restricted data, the System Administrator must have the ability to define security profiles down to the individual data field level.  Profiles must support read-only access and selective read/write privileges.  Security profiles must also be able to be assigned to individual devices such as workstations and printers.

Secure Platform Application: The Contractor must support deployment of host server and database security patches and service pack updates within one month of patch release (e.g., application running on Windows server Operating System (“OS”) should not limit installation security patches on host operating system).  Application and Contractor must support new operating system versions within one year of release.  Application security vulnerabilities shall be remediated with the development, testing and timely release of security patches by the application Contractor within three calendar months of the vulnerability being identified.

User Authentication/Single Sign-on (SSO): The City standard for a single point of user authentication is Microsoft Active Directory (“AD”), using the Lightweight Directory Access Protocol (“LDAP”).  The City standard for authentication is to allow properly authorized users to login just once on their computer and be able to access all approved applications during that active session.

Secure Authentication: All authentication activity occurring over the network should be encrypted using FIPS to ensure that logins and passwords are not transmitted in clear text.  This includes using FIPS 140-2 (at a minimum) and administrator authentication activity.

Sensitive Data: Applications containing or hosting sensitive data, as defined by State of California or US Federal law or regulation, shall encrypt data at rest, using (at a minimum) FIPS 140-2, data in motion over the network and all authentication activity.  Encryption algorithm used to encrypt data and authorization activity shall be industry standard.

Auditing and Logging: Application must log all security-related events including logon, logoff, data modification, data deletion, change in rights or permission levels, and the addition of data/information to the application.  Logs must include user ID generating the transaction, time of the transaction, and details regarding the activity (e.g., logon, logoff or data details).  System should support interoperability with centralized logging and Security Information Event Management (“SIEM”) technologies.

Compliance with Organization’s Security Policy, Standards and Procedures - Application Contractors working directly on City-owned applications or from City facilities are subject to all City policies, standards and guidelines.

Specific security information for the City’s Public Safety Network is provided in the “City Technology Standards” being provided as Attachment “A”.

### Application Security Coding Requirements

- Parameter Manipulation: Applications shall be designed to ensure that parameter manipulation does not provide access to data or application functionality that the user is not authorized to see or use.

- Input Validation: Sanitize all user input fields to ensure that cross-site scripting, SQL injection and other input related vulnerabilities are closed through secure application coding.  Input validation should be performed on the server/application and not on the client devices.

- Hidden Fields: System should not use “hidden fields” for Security.

- Cookies: System should not rely on cookies to define security settings.  Cookies must not contain or be used to obtain sensitive information.

- Session Identifiers: If system uses session identifiers, they should be generated with unpredictable numbers and should contain enough key space to prevent unauthorized use or guessing of the session ID’s.

- Error Messages: System should handle system errors in an appropriate manner.  Failed login attempts to the system should not generate detailed information about the failed login attempt (e.g., incorrect password or unknown user account).  Other security related errors (e.g., file not found, or permission denied) should generate generic error responses.  Detailed error information should be written to secure logs so that developers and system administrators have access to error details required to address the error.  Error messages should be clear.

### National & State Public Safety Data Standards

The US Federal government has taken the lead recently in developing standards for facilitating information sharing among local, state and federal first responders and emergency operations managers.  The proposed CAD, RMS and Mobile applications must comply and be maintained to these standards.

Deviations from the architecture and standards may represent a barrier to the implementation of the City’s public safety integration and interoperability goals and may be reviewed with prejudice.  All Contractors must specifically disclose all aspects of the proposed solution which deviate from the documented standards and desired architectures and provide approaches for consideration about the way non-standard components may be integrated.

The US Federal government, California Department of Justice and other parties, such as APCO, occasionally update and improve the referenced standards or develop new ones.  In that the City may adopt such future standards, it is mandatory that the CAD Contractor monitor these developments and upgrade their offerings as necessary to comply.

The time between purchase of a CAD system and its implementation may be significant; therefore, it is possible that updated standards may have been released in the interim.  The City will not accept products that will be outdated by the time they are implemented.  It shall be the Contractors responsibility to verify and validate all new standards as they are implemented.  The City shall not be responsible for determining when new standards are required.

Contractors are encouraged to review the standards and comply at minimum to the standards associated which each of the following:

NIBRS - National Incident Based Reporting System, CIBRS - California Incident Based Reporting System and UCR-Uniform Crime Report

Capture data to report official crime statistics to the Federal Bureau of Investigation under Uniform Crime Report (“UCR”), National Incident-Based Reporting System (“NIBRS”) and California Incident-Based Reporting System (“CIBRS”), once approved by California DOJ, implemented to improve the overall quality of crime data collected by law enforcement, captures details on each single crime incident—as well as on separate offenses within the same incident—including information on victims, known offenders, relationships between victims and offenders, arrestees, weapons, and property/evidence involved in the crimes.

https://ucr.fbi.gov/nibrs-overview

NIEM - National Information Exchange Mode

NIEM is a product developed by the Office of Justice Programs in the US Department of Justice and adopted by the US Department of Homeland Security.  NIEM describes XML schema for a variety of attributes associated with incidents and events including NCIC and NIBRS.  The schemas allow for the easy sharing of data among disparate agencies and are becoming the de-facto incident-based integration and interoperability standard.  Having CAD NIEM-compatible XML schemas available in a depository is required to improve the City’s ability to quickly respond to current and future data-sharing requirements.  The Contractor’s solution must specifically meet Global Justice Extensible Markup Language Data Model (“GJXDM”).

http://www.niem.gov/

http://it.ojp.gov/jxdm/

LEITSC - Law Enforcement Information Technology Standards Council

The LEITSC was established by the Office of Justice Programs in the US Department of Justice to foster integrated justice systems through the definition and implementation of standards of CAD and RMS systems.

https://it.ojp.gov/documents/leitsc_law_enforcement_rms_systems.pdf

https://it.ojp.gov/documents/leitsc_law_enforcement_cad_systems.pdf

NENA – National Emergency Number Association

NENA provides 9-1-1 policy, technology, operations and education standards for public safety communication centers.  The City has adopted the standards for ALI Data Exchange, ALI Response and GIS Mapping as a minimum standard.  As the technology advances, the City requires compliance for NG 9-1-1 standards as adapted by NENA.

https://www.nena.org/

Next-Gen 9-1-1

Contractor must be prepared to meet all existing and proposed Next-Gen 9-1-1 functionality, including VOIP, Voice to Text, Text to 911, Video Submission and T.D.D.  requirements.

http://www.its.dot.gov/ng911/

HIPAA - Health Insurance Portability and Accountability Act of 1996

HIPAA requires, among other things, that the privacy and security of protected health information be assured.  This includes such information as may be transmitted and/or stored by electronic systems, including via wireless telecommunications.  The CAD, RMS and Mobile systems must comply with the requirements of the law and the proposal must identify the steps taken to test and certify compliance with the standard prior to implementation.

http://www.hhs.gov/ocr/privacy/

CJIS Security Policy – Criminal Justice Information Services Security Policy

The CJIS Security Policy provides Criminal Justice Agencies (“CJA”) and Noncriminal Justice Agencies (“NCJA”) with a minimum set of security requirements for access to Federal Bureau of Investigation (“FBI”) Criminal Justice Information Services (“CJIS”) Division systems and information and to protect and safeguard Criminal Justice Information (“CJI”).  The CAD, RMS and Mobile systems must comply with the policy and the proposal must identify the steps taken to certify compliance with the standards prior to implementation.

http://www.fbi.gov/about-us/cjis/cjis-security-policy-resource-center/view

CLETS - California Law Enforcement Telecommunications System

California Law Enforcement Telecommunications System (“CLETS”) is an efficient law enforcement communications network available to all public agencies of law enforcement within the state.  The CLETS provides all law enforcement and criminal justice user agencies with the capability of obtaining information directly from federal and state computerized information files.  The CAD, RMS and Mobile systems must adhere to the statutes established in the CLETS Policies, Practices and Procedures publication.

http://oag.ca.gov/

RIPA – Racial and Identify Profiling Act

The Racial and Identity Profiling Act of 2015 (“RIPA”)(AB953) requires each state and local law enforcement agency to annually report to the Attorney General data on all stops, as defined, conducted by the agency’s peace officers, and require that data to include specified information, including the time, date, and location of the stop, and the reason for the stop.    The RIPA Board has established a requirement of reporting stop data by April 1, 2019. Specific required data elements are defined in Article 3. Data Elements to be Reports of the California Code of Regulations, Title 11. LAW, Division 1. ENFORCEMENT, Chapter 19, Final Text of Regulations.  The proposed systems must comply with the RIPA stop data reporting requirements no later than the earliest of the dates required by the RIPA Board.  Contractors must submit specification on how the proposed solution will collect all required data elements and how the data will be reported via a secure file transfer or web service to the California Department of Justice Stop Data Collection System (“SDCS”)

https://oag.ca.gov/sites/all/files/agweb/pdfs/ripa/stop-data-reg-final-text-110717.pdf?

APCO - The Association of Public-Safety Communications Officials

APCO is an international leader committed to providing complete public safety communications expertise, professional development, technical assistance, advocacy and outreach to benefit and the public.  APCO is an American National Standards Institute (“ANSI”)-Accredited Standards Developer (“ASD”) that develops standards for public safety communications.  The CAD system must comply with these standards and the proposal must identify the steps taken to certify compliance with the standards.

https://www.apcointl.org/

## CAD Software Requirements

The City requires the proposed CAD solution to be fully integrated with RMS and Mobile, with neither of these systems provided by a third party.  The CAD solution must meet the same general requirements as depicted in “Section 1.4, General Software Requirements”.

The proposed CAD system shall facilitate incident response and communication with operations in the field.  The system allows operations and communications to be augmented, assisted, or partially controlled by atomization that includes the ability for computer-controlled resource dispatching, resource status management, incident reporting and analytical information.  The system must be optimized for rapid response time and system reliability.  Because time is of the essence, the system must accurately provide a date and time-stamp for every activity.  The system must be capable of interfacing with more than one RMS system and support the exchange of data between other agency CAD systems.

The CAD solution must be designed to conform to the national standard for computer aided dispatch functional specifications, Unified Computer-Aided Dispatch Functional Requirements (“UCADFR”), developed by the LEITSC and the Law Enforcement Information Sharing Program (“LEISP”) technical standards of the U.S.  Department of Justice’s (“US DOJ”) Global Justice Extensible Markup Language (“XML”) Data Model (Global “JXDM”).

https://it.ojp.gov/documents/LEITSC_Law_Enforcement_CAD_Systems.pdf

For all exchanges generated by CAD, conformance with US DOJ’s Global JXDM is required.

The City desires a hosted or cloud-based system over a traditional server-client based solution requiring in-house expertise to support and maintain the infrastructure and software suite.

The CAD application must support complex, agency-defined resource recommendation algorithms that meet the needs of the public safety users.  Resource recommendations must be based on either AVL locations and/or Patrol Beat, depending on the event type.  The CAD application must maintain and track public safety resources by status and location provided by real-time AVL.

The CAD application must support complex event distribution based on event location, service agency, service type, and/or jurisdiction.  Certain event types must automatically create “linked” events for multiple agencies/services and distribute each to the appropriate dispatch position.

The systems must meet the following performance specifications as measured by maximum response time.  Response time is measured as the time between a user-initiated command via any mode and the return of the requested data or action from the system.  The system must (at a minimum) provide 99.999% uptime performance.

| Transaction | Maximum Response Time |
| --- | --- |
| Locally attached CAD workstations, no external data access | 1 second |
| Locally attached CAD workstations, geo-file validation required | 2 second |
| Locally attached CAD workstations, non-CAD data access required | 3 second |
| Locally attached Report Server, simple query | 2 second |
| Locally attached Report Server, complex query | 3 second |
| Standalone MDC computer, single record access | 1 second |

NOTE:  For each transaction listed, 95% of the occurrences must complete within the specified Maximum Response Time.

A workstation shall be deemed to be locally attached when it is in the same premise and on the same physical network as the application server.  All CAD workstations located in the PSAP will be locally attached on a 1GB network backbone with 100MB to the desktop.

The maximum response time for CAD queries that necessitate access to data sources outside the City’s computing environment, such as a mutual aid request or CLETS lookup, shall be measured as the response time provided by the external source plus three (3) seconds.

Response times for MDC computers shall be measured in standalone mode to discount any wireless network latency.

## MDC Software Requirements

The City requires the proposed Mobile solution to be fully integrated with CAD and RMS, with neither of these systems provided by a third party.  It is expected that the Mobile application will be an extension of CAD and RMS, providing the necessary functionality of a public safety user to receive and manage an incident and to further initiate and complete the reporting of an incident into the RMS system.  The Mobile solution must meet the same general requirements as depicted in “Section 1.4, General Software Requirements”.

The proposed Mobile system shall facilitate communication between operations in the field and the communication center, specifically for the atomization of notification of a Call for Service from the CAD to the MDC.  The CAD application’s Mobile component must provide the public safety user with real-time, incident-specific information.  Information must be accessible with minimal effort by the operator.  Routine queries and status functions must be form-driven or single function key/screen press, minimizing the need to type commands.

The Mobile environment must support multiple applications, such as mapping and field-based reporting while maintaining CAD status, messaging, and dispatch functionality as the primary operation.  Third party software applications must be able to co-exist on the same mobile hardware without impacting the performance of the Mobile solution.

The City’s MDC’s are configured with software to provide advanced authentication as required by the CLETS and the FBI CJIS Security Policy.  Specific details of the City’s mobile security standards are depicted in Attachment “A”, City Technology Standards, within this RFP.

The proposed solution must be fully capable of being deployed on the City’s existing hardware and operating system.  The City utilizes Panasonic CF-33, Getac F110 and Getac T800 ruggedized mobile computers for Police and civilian vehicles.  Each MDC are equipped with a GPS chipset and accesses the City’s secured network by Verizon Wireless as their public wireless carrier.

The proposed mobile solution must be capable of being utilized on a smart devices or similar functionality must be provided within an application to be used on a smart device.

## RMS Software Requirements

The City requires the proposed RMS solution to be fully integrated with CAD and Mobile and be developed as a native solution and not provided by a third party.  The RMS solution must meet the same general requirements as depicted in “Section 1.4, General Software Requirements”.

The proposed Law Enforcement RMS solution shall provide for the storage, retrieval, retention, manipulation, archiving, and viewing of information, records, documents, or files pertaining to law enforcement operations and cover the entire life span of records development, from the initial generation of the case file to its completion.  The RMS solution, at minimum, shall provide for the following business functions: calls for service, incident reporting, booking, investigative case management, property and evidence management, arrests, warrants, traffic accident reporting, citations, field interviews/contacts, registrants, pawns, civil process orders and restraints, permits and licenses, equipment and asset management, fleet management, personnel, and analytical support (crime analysis).

The RMS solution must be designed to conform to technical standards by the US DOJ Global Justice Extensible Markup Language (XML) Data Model (Global JXDM).

The RMS shall provide, at a minimum, the following general requirements: single entry (i.e., no duplicate data entry); automatic submission of data to external sources; maximization of the utilization of code tables; provide the ability to enter and query narrative(s)/text fields; spell check and formatting capability on narrative(s)/ text fields; provide the ability to access multiple systems from a single RMS workstation; utilization of a single database (virtual or physical); validation on data entry (i.e., logical edits, edit checks for all fields); and provide the ability for operators to generate inquiries to internal (i.e., CAD and RMS) and external data sources (i.e., CLETS, NCIC, DMV, LInX) from within each module where such inquiries make sense.

The proposed RMS solution must provide the operator with, at a minimum, the ability to reuse and/or import data returned from external sources to eliminate redundant data entry.  RMS must provide the capability to electronically forward RMS data to external data sources, either automatically or upon the user’s request (i.e., based on agency rules embedded within RMS).  The above capabilities should be based on existing and emerging criminal justice standards, including DOJ’s Global JXDM; the NIEM; and the National Institute of Science and Technology (NIST), including the Electronic Fingerprint Transmission Specification (EFTS) and Facial Recognition Collection standards.

The proposed RMS solution must have basic master indices that correlate and aggregate information in the following areas: people, locations, property, conveyances (e.g., vehicles), and organizations (including businesses and gangs).  Master indices eliminate redundant data entry by allowing the reuse of previously stored information and the automatic update of the master indices upon the entry of report information.  Master indices information should be captured in a variety of ways to include, at a minimum during the input of, information from an incident, traffic accident, vehicle reports, citation, booking, arrest, juvenile, fingerprint, and mug shot subsystems.  Prior to accepting an entry, RMS should automatically give the user the option of determining whether there is a match based on existing data.  The system should support the validation and linking of addresses, commonplace names, and street intersections.  Linkages among any information contained in the master indices (e.g., people to places or person to person) must be included in RMS.

The proposed RMS solution must be compatible with third party reporting tools such as Crystal Reports.  The City requires the solution to provide standard reports for Federal and State Statistical Reporting, including Uniform Crime Reporting (“UCR”) and National Incident Based Reporting System (“NIBRS”).

The proposed RMS solution must be capable of being utilized on an MDC and a smart devices or similar functionality must be provided within an application to be used on a smart device.

## Interface Software Requirements

The CAD/Mobile/RMS must be designed to operate as a component of a tightly integrated, comprehensive, multi-jurisdictional, multi-agency, multi-user, incident based public safety system.  Therefore, the proposed solution must interface with several of the City’s ancillary systems.  For each interface, all functionality will be fully described within a Functional Specification Document (“FSD”) that will be developed by the Contractor and approved by the City.  The FSD will be developed and approved after the Contractor is selected but before any work begins on the interface.  In the event a standard interface exists, the Contractor shall provide, in response to this RFP, the capabilities and functionality of each interface by submitting the FSD. Each interface, if appropriate, must operate from the CAD, Mobile, RMS & Smart Device platforms.

### ANI/ALI

An interface with the City’s Public Safety Answering Points ("PSAP”) software, VIPER® is required.  The interface must enable incoming E9-1-1 ANI/ALI data to be automatically mapped to corresponding address and phone data fields based on the Master Street Address Guide (“MSAG”) standard in the CFS event entry form and geo-locate the location of the caller on the CAD map display.  The interface must support all E9-1-1 ANI/ALI formats including wire-line, Wireless Phase I and Wireless Phase II, Voice over IP, and Multi-Line Telephone Systems.  The interface must enable the insertion of additional fields captured in the CFS event, including ESN, call type (landline, wireless), and ANI/ALI tracking ID (if available).

If the Contractor has an integrated PSAP software application as part of the CFS process, the integration shall be included as standard functionality and not be delivered nor implemented as a secondary option.

Next Generation 9-1-1 (NG-9-1-1)

The Contractor shall be responsible for progressive research and development of new technologies as they relate to NG-9-1-1 to be capable of receiving cellular calls, text messages, instant messaging, legacy 9-1-1 calls (wireline), telematics (automatic crash notification) data directly from the vehicle, VoIP calls, and live video feeds.  The Contractor shall include this functionality as standard functionality and not be delivered nor implemented as a secondary option.

The Contractor shall describe their vision, both immediate and long-term, for CAD-integrated Next Generation 9-1-1 services.  This should include a description of NG9-1-1-associated data management (receipt, case integration, storage and retention), as well as access for both CAD and mobile users.  The Contractor shall describe any NG9-1-1-related capabilities, functionality and features of the proposed CAD system, including any integration of NG9-1-1 data into the CAD call workflow.

To the extent that the functional elements of NG9-1-1 are defined, The Contractor is required to describe the proposed solution's ability to meet NENA i3 (08-002/08-003) and associated standards.  The City recognizes that current NENA standards do not specifically address core CAD functionality; however, it is clear that there are points of interaction with standardized i3 functional elements.  Contractor shall describe how the proposed CAD solution will be updated as new and revised standards, functionalities and features are developed, as well as how data elements from NG9-1-1 and CAD are managed to ensure data received from NG9-1-1 is usable without extensive reformatting by the CAD solution.

References:

http://www.its.dot.gov/ng911/

http://www.nena.org/?page=FuncIntrface_NG911

### Alarm Monitoring Company Public Safety Answering Point

The City is anticipating implementing an interface to provide the atomization between an Alarm Monitoring Company and the City’s Public Safety Answer Point (“PSAP”).   The proposed solution must be capable of establishing a bi-directional interface to to receive an initial notification of an alarm event and provide status updates by the PSAP to the initiating alarm company.  Bi directional updates may include the request for cancellation by the alarm company, updates by the key-holders information, notifications by the PSAP of the primary response aloing with associated status changes such as a unit being dispatched, arriving on scene and closing of the incident with disposition.

https://www.apcointl.org/resources/interoperability/asap-to-psap/asap-to-psap-protocol/

https://www.apcointl.org/download/alarm-monitoring-company-to-psap-cad-automated-secure-alarm-protocol-asap/?wpdmdl=5938

### License Plate Reader – Vigilant Solutions

The City Police Department uses a License Plate Reader (“LPR”) system by Vigilant Solutions.   Vigilant Solutions provides the capability to interface their technology with CAD to assist in automating alerts within CAD and/or the MDC’s for matches against various hotlists.   The proposed solution must provide the ability to interface with Vigilant Solutions Mobile LPR solution.

### Radio Console Interface / Push to Talk

The City utilizes Project 25 (“P25”) compliant fixed mount and portable radios by Motorola in conjunction with a Motorola MCC 7500 IP Dispatch Console.   The proposed solution must provide ability to display on a CAD workstation, the radio Push to Talk (“PTT”) IDs and EIDs (Emergency IDs) when received by the dispatcher for Police.  The IDs must include the Unit Radio Name (i.e.  100M or E1…etc.) and the location, by address or cross street as determined by GPS data provided by the P25 compliant radio.  In addition, the proposed solution must also display “Action Commands” as entered in the field on an MDC or other mobile device, i.e.  "Acknowledged”, "Enroute”, “Staged”, "Onscene”, "Clear”, "Change Location", etc.

### Global Positioning System (GPS) / Automatic Vehicle Location (AVL)

The City requires that the CAD/Mobile/Smart Device applications utilize the most current, real-time to near real-time location of each police vehicle and/or personnel.  Latitude and Longitude information needs to be converted to address data and appropriately displayed on the integrated CAD and Mobile maps.  The CAD and Mobile applications must be able to manually poll any GPS-equipped vehicle or person by assigned radio, MDC and/or Smart Device.  The CAD and Mobile applications must be configurable to control the automatic polling update rate based on location, status, time and/or distance, or any combination thereof.  GPS data is available from following:

Mobile Data Computers:  The City utilizes a Panasonic and Getac Rugged Tablet equipped with a built in GPS chipset in Police vehicles.  The system must be capable of being configured to track the location of the MDC as the primary method of receiving GPS data for vehicle location.

Radio System:  The City utilizes Motorola P25 compliant radios equipped with an internal GPS receiver and should be used as the primary, or secondary method of receiving GPS data.   The system should be capable of being configured to track the location of the portable radio if the portable radio assigned to an officer is not within a defined perimeter of the vehicle they are assigned to.

Cellular/Smart Devices:  The City utilizes a verity of cellular enabled smart devices to include, Apple IOS, Android and Windows based operating systems.  Most devices are equipped with Assisted GPS (A-GPS).  The system should be capable of being configured to track the location of the smart device assigned to an officer, and if necessary, be a secondary method of tracking the location of the assigned officer if the smart devices is not within a defined perimeter of the vehicle they are assigned to.

### Records Check System

The City requires an interface be implemented to provide the ability to access and complete either; queries, locating, entering, modifying, clearing, cancelling, and or commenting on records on multiple systems either individually, or a combination thereof.

The Records Check system must be capable of accessing; agency local databases such as CAD and RMS, state databases such as the CLETS and DMV, National Databases such as NLETS/NCIC, Local Databases such as the local Orange County Automated Telecommunications System (“OCATS”) system and the regional LInX and CopLink Databases.

In addition, the Contractors must provide their experience in completing each of the following interfaces and where applicable, provide the experience in working with specific applications that are depicted below.

### California Dept of Justice CLETS

The City requires an interface to; the CLETS for the purpose of accessing files of the CJIS, the Department of Motor Vehicles (“DMV”), the National Crime Information Center (“NCIC”), and the National Law Enforcement Telecommunications System (“NLETS”) over the California Department of Justice (“CA DoJ”) secure telecommunication backbone.  Connectivity to the CLETS is through the Orange County Sheriff’s Department’s OCATS message switch.  The Orange County Sheriff’s Department is the CLETS Direct Interfaces System Host for Orange County.

The interface shall be designed to handle all CLETS traffic; transmitting and receiving responses to inquiries, entries and updates, and the processing of administrative messages such as All-Point Bulletins on a statewide or nationwide basis.

The CLETS interface must provide for all data forms currently available for the CLETS system to complete queries, locating, entering, modifying, clearing, cancelling, and or commenting on records including LoJack records.  The interface must be able to “nest” queries (example, when a registered owner’s information is returned from a vehicle tag query, the system automatically runs the registered owner’s information, etc.).

The interface will present the returned CLETS information in a formatted display with capability to add specific returned information as a supplement to the CAD incident or RMS record, or be forwarded to an MDC or smart device application.  The proposed solution will also provide for the display of images (mug shots, driver’s license or ID photos, etc.).

The interface shall provide the ability to “spawn” additional queries based on the information returned from a previous query to any other interfaced database.  The ability to generate spawned queries shall be configurable by a system administrator (example, when a return from CLETS is received and the info contains the name of an individual, the system shall spawn an additional query to the regional LInX database).

The proposed solution should provide the ability to perform multiple simultaneous searches from a single-entry screen form (i.e.  with a single entry of identifying information in a query) and automatically search CLETS, NCIC, DMV, local databases via OCATS, and the resident CAD, RMS and BOLO files, etc.

### Orange County Automated Telecommunications System (“OCATS”)

The Orange County Sheriff’s Department maintains a message switch, known as OCATS for local subscribing agencies to inquiry and update records within the local Automated Jail System (“AJS”), Automated Warrant Services System (“AWSS”), and the Local Arrest Records System (“LARS”).  The  City intends to maintain its direct interface with OCATS for performing queries of the local systems similar to the CLETS system.   OCATS has established an established protocol for CAD and RMS providers.  The proposed solution must provide for the simultaneous query of both CLETS and the OCATS system.

### Law Enforcement Information Exchange (“LInX”)

The City is a participating member of the So Cal LInX Region.  LInX is a national cooperative law enforcement data share consisting of participating members of municipal, county, state and federal law enforcement agencies broken down into 12 regions, primarily in jurisdictions with military bases nearby.

The LInX database consists of law enforcement data to include: Incident Reports, Accident Reports, Warrants, Arrest Reports, Booking Records, Field Interviews/Contacts, Pawn Shop Records, Citations, Traffic Stops, Sexual Offender Registry, Mugshots, Photo’s Associated with Record Types, Narratives and Supplemental Narratives.

LInX has established a web service interface using NIEM-based LEXS S/R standards, specifically, Global Justice Extensible Markup Language Data Model (“GJXDM”).

http://it.ojp.gov/jxdm/

The proposed solution must provide the ability to export data to the LinX system with the ability to control what data and when the data will be sent with the ability to restrict sensitive data. In addition to providing data to LInX, the City intends to have a direct interface with LInX for performing queries of the LInX database similar to queries of the CLETS system.  The proposed solution must provide for the simultaneous query of both CLETS and LInX.

### California Dept of Justice - Cal-Photo

The California Department of Justice (“DOJ”) Cal-Photo application provides law enforcement users with the ability to search and retrieve DMV images from DMV, and Mugshot images from the various connected Law Enforcement Agency (“LEA”) image databases throughout California.  These images are instantly available through an XML for a computer to computer interface using a custom interface.  The proposed solution must provide for the simultaneous query of Cal-Photo in conjunction with CLETS queries.

### California Dept of Corrections and Rehabilitation - Parole LEADS

The CDCR has an externally published web service to enable law enforcement agencies the ability to automate inquires via a Simple Object Access Protocol (“SOAP”).  The proposed solution must provide an option to simultaneously query the Parole LEADS system in conjunction with CLETS queries.

### Forensic Logic (formerly CopLink)

Similar to LinX, the City is a participating member of CopLink.  CopLink, now owned by Forensic Logic, is a data sharing and crime analytics platform designed to help law enforcement organizations by providing tactical, strategic and command-level access to vast quantities seemingly unrelated data.

https://forensiclogic.com/platform/

The CopLink database consists of law enforcement data to include: Incident Reports, Accident Reports, Warrants, Arrest Reports, Booking Records, Field Interviews/Contacts, Pawn Shop Records, Citations, Traffic Stops, Sexual Offender Registry, Mugshots, Photo’s Associated with Record Types, Narratives and Supplemental Narratives.

The proposed solution must provide the ability to export data to the CopLink system with the ability to control what data and when the data will be sent with the ability to restrict sensitive data. In addition to providing data to CopLink, the City intends to have a direct interface with CopLink for performing queries of the CopLink database similar to queries of the CLETS system.  The proposed solution must provide for the simultaneous query of both CLETS and CopLink.

### Crossroads Software – Citation, Analytics and Report Writing

The City utilizes Crossroads Software for citations and collision reports.  The software provides for analytics and report writing functions.  Crossroad provides a desktop application as well as a mobile application on a handheld device with Microsoft Windows Mobile Operating System.  Data from these devices is synchronized with a centralized server which is interfaced with the Orange County Court.  The proposed solution must provide the ability to interface with Crossroads for ingesting Citation and Accident data elements, and associated attachments to a report to include file formats consistent with pictures and portal document format (“PDF”).  LJTEapon4jsf

If the proposed solution includes an Accident and/or Citation module as part of the solution, the Contractor should provide details of the functionality and whether the module can be run on a hand-held device utilized in the field.   An interface with Orange County Courts will be required.

### License Plate Reader – Vigilant Solutions

The City Police Department utilizes a License Plate Reader (“LPR”) system by Vigilant Solutions. Vigilant Solutions provides the capability to interface their technology with CAD to assist in automating alerts within CAD and/or the MDC’s for matches against various hotlists. The proposed solution must provide the ability to interface with the LPR solution to alert dispatchers and patrol officers on a hot hit from a stationary trailer or vehicle mounted reader.  Upon recognition of a hot hit, the CAD system will receive the location of reader at the time of the hot hit, and the captured photo and an indication of the status of the plate, whether lost, stolen, or if the vehicle is wanted or of interest.  Upon receipt of a hot hit, the CAD system must complete an automated CLETS query.  The CAD system must create a call for service/incident, utilizing the location provided by the hot hit, and if from a vehicle mounted reader, assign the unit to the incident.   Further requirements will be defined in an interface functional specification.

### California Highway Patrol - Allied Agencies to SWITRS Reporting Services

The California Highway Patrol (“CHP”) Allied Agencies Reporting Service (“AARS”) has developed a system for Allied Agencies (“AA”) to transmit collision data electronically to the CHP Statewide Integrated Traffic Records System (“SWITRS”) by way of a web service known as AARS Web (Collision) Reporting Service.  The proposed solution must provide the ability to interface with the AARS Web Reporting Service for electronic submission of collision data.

### LiveScan

The City utilizes live scan hardware to capture and store biometrics that includes fingerprints, data and an mugshot to the regional Cal-ID system.  The proposed solution must provide the ability to interface with the live scan hardware to provide data required by the live scan system to eliminate the need to manually re-enter data.  In addition, the interface must be capable of ingesting a mugshot provided by the live scan system and associating it with master name record the RMS.

### Lexis Nexis – Desk Officer Reporting System

The City has implemented a citizen self-reporting system called Desk Officer Reporting System (“DORS”) by Lexis Nexis.  The DORS system is exposed to the citizens by way of the City’s website.   The City is currently allowing citizens to submit report on: attempted thefts, petty theft, mail theft, vandalism and vehicle tampering and allowing citizens to file for a bicycle license or request patrol checks for home while vacationing.  The proposed solution must be capable of ingesting the information from the DORS system and created associated calls for service and case files within the RMS system.

https://risk.lexisnexis.com/-/media/files/government/dors_brochure-pdf.pdf

### Orange County District Attorney – Electronic Direction for Compliant

The City is interested in interfacing directly with the Orange County District Attorney (“DA”) to submit arrest and case information electronically to the DA’s Case Management System via their Electronic Directions for Complaint (“EDC”) interface.  The DA’s IT Department is currently developing an API for the interface.   The proposed solution must be capable of sending arrest and case related information to the CA and provide the ability for a user to determine the data and associated case reports and attachments to be sent.  Given this interface is new to the DA, the DA may be open working the CAD/RMS provider to comply with a current interface deployed.

### Video Management System

The City utilizes an array of camera systems and has access to private camera systems throughout the City.  The proposed solution must be capable of integrating with these systems to provide a display of the physical location of each camera, the cameras field of view, and provide a link to access and display the live feed of the selected camera or cameras.

### Body Warn Camera / Dash Mount Camera Metadata Tagging

The City currently utilizes dash mount camera and will be deploying body-warn cameras in the near future.  The proposed solution must provide an interface to provide data to be utilized for tagging videos.  Data element should include the incident ID, type of incident, location of incident, the unit(s) assigned to the incident, the personnel assigned to the incident, and time stamp to be utilized to associate status changes during the incident.  Further requirements will be defined in an interface functional specification.

### CAD-to-CAD Interface

The purpose of the CAD-to-CAD interface is to connect disparate CAD systems for the purpose of exchanging data to assist in the transfer or receipt of a call for service of neighboring police agencies and to allow the transfer of each agencies resources location and status information.

The proposed interface functionality, whether a single instance for multiple CAD system or a single instance for each CAD connection, must be capable of, but not limited to, the following: establishing a heartbeat to monitor the connectivity of the two systems; sending and receiving incident data; establishing a link between the incidents on either end for updates; acknowledgment of receipt of an incident; assigned resource identification and corresponding status changes of each assigned resource; resource position (GPS) or location sharing; incident cancellation processing; request for shared resources; and messaging between the two CAD systems.  The interface shall provide an audit trail of the exchanged information to enable research by way of querying the data.

Ideally, the CAD-to-CAD interface in its basic function is a single data exchange switch facilitating the exchange of data between each of the disparate CAD systems to enable a dispatcher on either end of the interface to visually monitor the current location and status of neighboring agencies resources and to enable the CAD system to make resource response recommendations based on the known real-time location and proximity of the resources, regardless of which agency the resource belongs to.  Initiation of the request for resource response shall be automated by sending incident information and the requested resources to the neighboring agency’s CAD system.  Upon receipt, the receiving dispatcher shall manually accept or deny the request and manage the dispatching functions resident to their CAD system.

The City requires an interface for each of the following agencies:

- Orange County Fire Authority (“OCFA”).  The interface would be with Tellus (formerly FatPot) which is interfaced with the OCFA TriTech CAD system.

- Orange County Sheriff’s Department (“OCSD”0.  The interface would be direct with the agency’s TriTech CAD system.

### Tow Provider Interface

The City currently contracts with several tow providers and utilizes a rotation process to identify which provider is to be utilized when a request for tow is initiated.  The City desires an output from the CAD for service requests that could be sent via an email, a page or SMS text, a fax, or an interface to the two provider CAD system.  The City may, in the future, integrate with a regional system dispatching and tracking system.   The proposed solution must provide the capability of a notification at minimum.  Further requirements will be defined in an interface functional specification.

## System Testing, Reliability and Acceptance

The City requires a system acceptance process comprised of at least the following components; the System Test Period, the System Reliability Period, and the Final System Acceptance as described further below.  During the System Test Period and the System Reliability Period, if the system reveals any major defects or several minor defects impacting the completion of testing and/or production use of the system, the process shall be terminated, and the Contractor shall reasonably resolve outstanding issues.  Once the issues have been addressed, the Contractor will recommence.  The Contractor shall describe its trouble reporting, priority, and severity plan for this process.  The Contractor shall describe responses to failed user acceptance tests, including when the testing must be held in abeyance, and recommenced in its entirety from the beginning as may be required by the City.

### System Test Period

The Contractor’s software will be delivered to the City accompanied with written documentation stating the system is ready for testing and a draft acceptance test plan (“ATP”) for the City to use in its acceptance testing process.  The City will review the written draft of the testing plan and schedule the installation of the software within the City test environment.  The acceptance test period will begin when the City, along with the assistance of the Contractor, first performs all tests in accordance with the ATP and successfully completes the tests.  If major defects or numerous minor defects are found during the acceptance testing, the tests shall be terminated, and the Contractor shall resolve outstanding issues.

Once all issues have been addressed, the Contractor will recommence the ATP process, in its entirety, from the beginning as may be required by the City.

The Contractor shall provide the City with draft test plans that include, but is not necessarily limited to the following:

- Drafting a test plan for City staff;

- User acceptance testing;

- Product performance testing;

- Interfaces testing;

- Security testing;

- Data conversion testing;

- Hardware and network capacity testing;

- Integration testing;

- Load testing; and

- Fail-over testing.

The City shall be responsible for conducting a final unit, subsystem, and system acceptance test that will include, but is not necessarily limited to, the following:

- Testing all software components in accordance with published functions and features;

- Testing all software components;

- Testing all system software based on business scenarios;

- Testing all system software based on user friendliness;

- Testing of all contracted interfaces based on design and business scenario;

- Parallel testing prior to cutover (if parallel processing is appropriate);

- Security testing;

- Data Conversion testing;

- Testing based on business scenarios;

- Hardware and network capacity testing;

- Integration testing;

- Load testing; and

- Fail-over testing.

The Contractor shall review the City’s additions to the test plans for accuracy and completeness.  The City reserves the right to revise the test plans provided that reasonable notice is given to the Contractor.  The City maintains sole authority to certify the successful completion of any and all tests performed by the Contractor on the proposed system.

### System Reliability Period

After the successful completion of the cutover period, there shall be a minimum of sixty (60) day reliability testing during which the newly installed system will be in production and its performance monitored.  During this period, the system must perform fully without degradation of any kind for the System Reliability Period to be satisfied.  If any major defects or numerous minor defects are discovered, the System Reliability Period shall be terminated, and the Contractor shall resolve all issues.  Once all issues have been addressed, the Contractor will recommence the System Reliability Period, in its entirety, from the beginning as may be required by the City.

Severity levels pertaining to the system are defined as:

Severity Level 1 (S1): Critical system errors, which are defined as: Loss of Data, Corruption of Data, or Loss of Productive Use of the System.  In the event this type of error occurs, the City will immediately notify Contractor and the ninety (90) day Reliability period will be cancelled.  Contractor personnel shall promptly resolve the problem at no additional cost and a new ninety (90) day Reliability period will begin.  Once the system operates for 90 consecutive days without a Severity Level 1, the ninety (90) day Reliability test will be completed.

Severity Level 2 (S2): Critical errors exist when the primary purpose of the Contractor’s CAD/Mobile software is compromised, and productive use of the system is significantly impacted.  A procedural workaround is either not immediately or readily available or has been proposed and has been found to be unacceptable by the City.  In the event this type of error occurs, the City will immediately notify the Contractor and the thirty (90) day Reliability period will be suspended.  The Contractor’s personnel shall promptly resolve the problem at no additional cost to the City, and the ninety (90) day Reliability period will re-commence at the point where it was suspended.

Severity Level 3 (S3): Non-critical errors which are defined as incomplete operation of system where a procedural workaround is readily and immediately available, and productive use of the system is not significantly impacted on software or operations.  In the event this type of error occurs, the City will immediately notify the Contractor, but the ninety (90) day Reliability period will continue.  If possible, the Contractor shall resolve the problem during the ninety (90) day Reliability period, but if necessary, resolve in a future bug fixes release of the product.

Severity Level 4 (S4): Cosmetic errors which are defined as configuration issues that can be corrected by the City, data integrity issues that must be addressed by the City, Help File documentation errors, or enhancements that can be made in the future to the presently installed system.  Severity level 4 defects will be remedied within a future software fixes release.

### Final System Acceptance

At the successful completion of the System Reliability Period and completion of all data conversions, and demonstration they system backup and recovery features function successfully, the City shall issue final acceptance certificate.

## Hardware Requirements

All hardware must be new equipment delivered in the manufacturers’ original packaging and carrying the manufacturers’ full warranty.  The warranty period begins after system acceptance and certification by the City that the equipment is in production use.  All equipment must be installed according to manufacturers’ requirements.

All hardware components must be sized appropriately to ensure that the performance requirements of the Contractor’s application will be met.  Equipment specifications provided by the City within this RFP shall be considered as minimal requirements.  All servers provided by the Contractor will, at a minimum, meet the City Technology Standards as outlined in Attachment “A” within this RFP.

Contractor must provide servers and workstations that meet the following minimum requirements:

### CAD Servers:

The Contractor shall furnish and install the necessary Servers to support the CAD and all Interfaces and Report Server(s).  All server architecture must comply with the City's IS Technology Standards provided in Attachment “B” in this RFP, and leverage VMware's virtualization technology and Industry Standard 3rd Party Automated Tools to facilitate high-availability and immediate failover from a network, computer, and storage layer.

The Contractor will recommend the quantity and provide such servers as to meet or exceed the minimum requirements of their software and the required performance standards delineated within this RFP.

The operating system kernel may not be modified.  All support for hardware redundancy must be provided by Contractor-supplied middleware and firmware that can be upgraded as required.

The solution must provide the guaranteed availability of 99.999% uptime (at a minimum), utilizing fully redundant hardware i.e., functionally critical hardware within the single server must be duplexed.  Interface and Report Servers are not required to be fault tolerant.  For the primary CAD servers, the following components must be fully redundant, at minimum:

Motherboard, including CPU chipsets and Memory DIMMs

The motherboards must be completely encased for safety, and designed to allow insertion and removal, for repair, without shutting down the operating system, or the applications.

Disk Drives

All disk drives in the proposed solution must use RAID 1 mirroring (at a minimum).  This data protection must be provided with redundant SAS controllers that perform all Input/Output (“I/O”) operations across a redundant bus.  The mirror technique must be implemented in a fashion that has no performance penalty.  All disk drives must be completely encased for safety, and designed to allow insertion and removal, for repair, without shutting down the operating system, or the applications.

Power Cords

Two external, twist-locking power cords are required for the proposed solution.  The server must have onboard dual power supplies with dual power cords connected to two separate and distinct Uninterruptible Power Supplies connected to two separate power circuits.

For security reasons, all encased components must be designed so that City personnel and/or operational staff can be trained in the replacement of failed parts.  Replacement parts must be shipped to the City utilizing a priority overnight carrier with guaranteed delivery.

The proposed server solution must contain self-diagnosing logic that will determine, based on error thresholds, if a component is failing.  Once that determination is made, and without human intervention, the server must be capable of contacting the supplying Contractor and requesting replacement components.

The Contractor will maintain a support infrastructure that is fully operational 24 hours per day, and seven days per week.  This infrastructure must be global in nature, and also accept calls from City personnel as they have questions or issues pertaining to the proposed solution.

### Workstations

The Contractor shall furnish and install six (6) workstations to support the Operations, Training, and Testing environments.  The Contractor will provide such workstations as to meet or exceed the minimum requirements of their software and the required performance standards delineated within this RFP.  All workstation architecture must comply with the City’s IS Technology Standards as outlined in Attachment “A” within this RFP.

### Position Requirements

- Eight (8) – Combination Dispatch and Call Taking Positions

- Site License – Mobile Computers

- Site License – Browser Based Functionality

- Site License – Police Records Management System

- Site License – Records Check System

### CAD Printers

The Contractor shall provide two (2) laser printers to support the printing of reports.  The printer must have a network interface controller (“NIC”) installed.  All printers, at a minimum, must comply with the City’s IS Technology Standards as outlined in Attachment “A” within this RFP.

## Licenses

Contractors shall provide a copy of all end user software license agreements (“EULA”) that they will be requesting the City to execute.

## Maintenance, Support and Updates

The Contractor shall make available to the City all updates to the software, as they are released, at no additional charge, so long as the City is currently under the Contractor’s software maintenance agreement.  To ensure that documentation is consistent with the operating environment, updated documentation must be delivered concurrently with the software update.

## Warrant

The Contractor shall include in its proposal a list and description of warranties provided, including, but not limited to:

- Warrant of Performance – one-year performance warranty covering the specifications for and performance of all software and services, commencing upon system acceptance;

- Warrant of representations made by Contractor in response to RFP;

- Warrant Against Viruses – Contractor warrants against deliberate time bombs – encrypted key technology to disable the system or otherwise hinder system functionality;

- Warrant of Contractor Capability – Contractor is financially viable and there are no legal proceedings against the Contractor that could jeopardize this agreement;

- Warrant of Past Success – System is installed and running at other similar locations, and there is no pending litigation against the Contractor based upon problems with the system and Contractor performance;

- Configuration Warrant – Contractor warrants that the system provided and installed includes all components necessary to perform the processing presented; and

- Release Warrant – Contractor warrants the combination of hardware, software, and operating system requirements.

- Product Continuance Warrant- Contractor warrants the continuance of their product including incorporating state and federal mandates, and/or the ability to transition without cost to their refreshed product line.

## Quality Control

This RFP requires the establishment of a quality control system by the Contractor to ensure that hardware and software supplies and/or services meet the quality standards explicitly and implicitly specified in this RFP.  The quality control system, including procedures, is subject to surveillance by the City.

The quality control system and procedures shall be designed by the Contractor.  The Contractor’s procedures used to implement the requirements of this sub-specification shall be subject to the approval of the City.  In the event of disapproval, the Contractor is solely responsible for devising new procedures that meet with the explicit approval of the City.

The quality control system shall ensure that adequate control of quality is maintained throughout all areas of contract performance, including, as applicable, the receipt, identification, stocking, and issuance of material; the entire physical process of manufacture, packaging, shipping, storage, installation, and maintenance; and processes of software development including design structure, coding, testing, integration, and implementation.

All equipment, supplies, and services under the contract, whether manufactured or performed at the Contractor’s facility or at any other source, shall be subject to control at such points as necessary to ensure conformity with the specifications and contractual requirements.  The proposed solution shall provide for the prevention and ready detection of discrepancies and for timely and positive corrective action.  The Contractor must make objective evidence of quality performance readily available to the City.

Attachment A:  City Technology Standards

The City maintains a segmented Public Safety Network (“PSN”) operated by the Information Technology (“IT”) Department.  The IT Department has established general standards and best practices for the components that make up the various systems deployed with Public Safety as follows;

Network Environment:  A segmented public safety network is maintained and operated by the IT Department.  Each agency within the public safety network is further isolated into VLAN’s into two functional disciplines, Police and Communications, to ensure access to protect data is secure.  I.e., CJIS data vs HIPAA data, etc.

The segments and VLAN’s are isolated behind SonicWALL Firewalls (“FW”).  The PSN has interconnections with other public safety agencies locally and at the County and State via many different mediums including VPN, Point-to-Point and LAN-to-LAN connections.  All layer three switches are VDX 6740/7750 and ICX 6610 series Enterprise-Class Brocade Switches.  All firewalls are SonicWALL SRA Series 4600 firewalls.

Network Access and Security:  The City has deployed as its standard, Microsoft Enterprise Endpoint Protection, to impose two standards that encompass security on desktop computers, mobile computers and servers.  Desktop and mobile computers require Microsoft’s Windows Defender Security Center software to be loaded.  This software acts as the anti-virus and malware software.  Also required is Windows Defender Security Center on all servers that serve information to computers such as a file server.

Users are authenticated on both stationary desktop computers and mobile computers by Windows Active Directory.  For stationary desktop computers, user’s login using the standard Windows login and once the user’s credentials are verified; the user arrives at the Windows desktop.

MDC traffic is using Windows 10 OS firewall and encrypted by NetMotion using 256 AES encryption.  Generated traffic is sent across the commercial wireless carrier (Verizon and AT&T) to the PSN through a dedicated circuit into Cisco routers.  The routers are then connected to the CAD VLAN segment which has access to the Cal DOJ CLETS via a Point-To-Point connection.  The CAD system has access to the same VLAN via the COM router server.

The Cal DoJ CLETS information is accessed via the CAD server by an MDC via the CAD client.  NetMotion client is used to encrypt/decrypt the communications between the MDC and CAD VLAN.  No CLETS data is stored on the MDC hard drives.

MDC, Tablet and Smartphone users will utilize NetMotion Mobility Client to secure a VPN connection via the agency’s wireless network provider, Verizon and AT&T, with the agency’s secured network for accessing the CLETS.  NetMotion works in conjunction with a CJIS compliant 2-factor authentication provider, Rapid Identity (formerly 2FA) using RFID cards in combination with NetMotion to accomplish “something you know”; username and password, with “something you have”; an access card.

There is a tertiary authentication that occurs between the MDC, AD, Microsoft Certificate Authority (“CA”), and Microsoft RADIUS.  This authentication is called machine authentication.  After the computer joins the Domain, the computer object in Active Directory is moved to the appropriate Organizational Unit (“OU”).  The object then authenticates against RADIUS and the CA issues a valid certificate.  This entrusts that the computer that has VPN access through NetMetion identifies as an authorized computer to then access network resources.

Time Synchronization:  The City synchronizes system time to an NTP server.  Windows utilizes a time service called ‘Windows Time’, which is automatically installed in the service list.  The program executable is ‘w32time.exe’.  The service is installed and enabled by default during installation.

Windows Domain Networking is deployed, and only the Primary Domain Controller (PDC) synchronizes with the time reference.  All other servers and workstations in the domain sync to the PDC using Windows proprietary protocol.  The default installation procedure automatically configures workstations and servers to sync to the controlling PDC.  Only the PDC needs to be configured to synchronize to an external time reference.  The City currently sync to the following url: north-america.pool.ntp.org.

All servers, workstations, MDCs and Brocade/Cisco network equipment are setup to sync with the City’s PDC.  Mobile devices like phones and tablets use the cellular provider network to sync their clocks.

NetMotion Mobility: By F-Secure Corporation (NIST Cert# 237, 441, & 493, FIPS 140-2 Certified) provides the secure VPN tunnel with end-to-end security standards-based encryption to FIPS 140-2 validated AES encryption.

Software Updates:  The IT Department utilizes Microsoft’s System Center Configuration Manager to deploy software to each desktop computer, mobile computer and server on the network.  IT uses the same software to provide operating system software updates to these resources as well.  IT defines this process as “Patch Tuesday” in which updates are sent out to affected systems that receive the updates once a month.  When a threat is recognized prior to the standard Patch Tuesday interval, IT staff triggers the system to perform the update at that time, rather than waiting for the next Patch Tuesday.

Desktop Hardware and Operating System Software:  The City standardizes with Dell Optiplex Desktop computers with Windows 7 Pro-64-bit, Windows 8.1, and Windows 10.  The City is phasing out older Lenovo desktop computers.  The PC should have a minimum Intel Core i5 3.2GHz processor, 8 GB of RAM, a 500 GB HDD and a DVDRW.  Each computer is equipped with Dell/Lenovo monitors varying from 17 inch to 24 inch models.

The City replaces desktop computers on a 5-year cycle and the monitors on an as needed basis.  For the purpose of the CAD, RMS and Mobile Replacement Project, the City has held off replacing the hardware within the Communication Center until a Contractor has been selected and specific requirements are determined.

Server Hardware and Operating System Software:  The City standardizes with Dell FX/FC hosts and Hyper-V software for the virtual servers.  The servers’ operating system ranges from Microsoft Windows 2008 to 2016.

The City replaces physical servers on a 7-year cycle.  For the purpose of the CAD, RMS and Mobile Replacement Project, the City has held off replacing the hardware for CAD severs and ancillary interface servers until a Contractor has been selected and specific requirements are determined.

Mobile Hardware and Operating System Software:  The standard hardware is the Panasonic CF-33 Rugged Tablet; 12in Display, 5MP Camera, Intel i5-6300U 2.4GHz Processor, 16GB RAM, 500GB SSD, 1200 NITs Touchscreen Display, Dual batteries, 5MP camera, 802.11AC Wireless, Bluetooth, TPM, GPS built in receiver, 4G.LTE Broadband (Multi Carrier).  Each tablet is configured to run Windows 10 enterprise 64-bit.  BitLocker provides full disk encryption.

The City replaces mobile computers on a 7-year cycle.  For the purpose of the CAD, RMS and Mobile Replacement Project, the City requires the Contractor to ensure their mobile applications are capable of being installed and perform as designed without any degradation.

Mobile Smartphone’s:  The City standardizes on Apple iPhone 7x and 8x with an iOS operating system.

Mobile Device Management (“MDM”): The City utilizes Microsoft Intune cloud-based enterprise mobility management software as an MDM for all mobile devices.  Microsoft Intune provides over-the-air centralized management, diagnostics, and monitoring for the mobile devices managed by the City.  The City primarily uses Microsoft Intune for Cell Phones.  Microsoft Intune monitors each device, showing useful metrics such as client hardware/software information, location of each device, and remote lock and erase devices.  The following is the extent to which Microsoft Intune is utilized by the city; push applications to devices, manage user mail exchange credentials, track location of lost devices, and remote lock or wipe of stolen devices.

Back-Up and Recovery Software and Process:  The City currently backs up the existing CAD and RMS system using Carbonite’s eVault solution.  The method of backup is disk to disk to cloud backups.  The data is stored on the City’s eVault appliances located at the City Hall datacenter and identical copies are sent to the cloud for offsite storage.

City Telephone System:  The City has deployed a Voice over Internet Protocol (“VoIP”) enterprise telephone system from Cisco.  The system utilizes the Cisco Call Manager version 11.  The Cisco system is locally hosted on a virtual server and utilizes PRI trunks.  The system is SIP compatible and provides legacy analog functionality.  The Cisco system supports 500+ phones for the City, to include standard features such as voicemail, call forwarding, conference calling and more.

Attachment B:  City GIS Standards